## Dashboard
DPDP Act 2023 Remediation Tracker
Carzonrent India Pvt Ltd. Built from 13 HOD interviews, 8 to 14 October 2026.
Programme start date | 2026-10-14 | Input. Changing it moves every action due date.
Main DPDP duties start (approx.) | 2027-05-13 | Input. 18 months from 13 Nov 2025 notification; Legal to confirm.
Days remaining | 211
Findings |  |  | Theme | Gap | Verify | Open
Total findings | 58 |  | Messaging channels | 5 | 0 | 5
Confirmed gaps | 36 |  | ID masking | 3 | 2 | 5
Items to verify | 22 |  | Local copies | 8 | 2 | 10
Closed | 0 |  | Retention | 5 | 8 | 13
Open | 58 |  | Vendor DPAs | 5 | 2 | 7
% closed | 0% |  | Notice & consent | 2 | 2 | 4
|  |  | Cross-border | 0 | 5 | 5
Actions |  |  | Sharing & minimisation | 5 | 0 | 5
Total actions | 11 |  | Consent | 1 | 0 | 1
Complete | 0 |  | Physical records | 1 | 0 | 1
In progress | 0 |  | Incident response | 0 | 1 | 1
Blocked | 0 |  | Data accuracy | 1 | 0 | 1
Overdue | 0 |  | Total | 36 | 22 | 58
Average % complete | 0%
Departments by preliminary rating
Critical | 2
High | 6
Medium | 4
Low | 1
HOD declarations signed | 0 of 13
Retention schedule
Data categories scheduled | 24
Approved by Legal | 0
Implemented in systems | 0
Statutory floors | 4
Proposed, no statute found | 13
How to use
Blue text on yellow cells are inputs. Everything else calculates.
Update Status in the Gap Register and Action Tracker; this page recalculates.
Set a named owner and evidence link on each action. Change a target day on the Action Tracker to re-plan.
Assumptions and sources are on the Lists sheet. Retention law summary is on the Retention Rules sheet.

## Gap Register
Gap Register
One row per finding. Yellow cells are for the team to update. Target date comes from the linked action.
ID | Department | Theme | Finding | Type | Priority | DPDP reference | Source | Action ID | Status | Target date | Named owner | Evidence / remarks
G-001 | VRM & Billing | Messaging channels | DL, Aadhaar, RC, insurance and phone numbers collected on personal WhatsApp after hours; allocation shares bookings there at peak. | Gap | Critical | s.8(5); Rule 6 | VRM & Billing HOD interview, 08 Oct 2026 | A1 | Open | 2026-11-13
G-002 | Fleet | Messaging channels | Vendors send KYC documents over WhatsApp as well as through CabPro. | Gap | High | s.8(5); Rule 6 | Fleet HOD interview, 08 Oct 2026 | A1 | Open | 2026-11-13
G-003 | KAM | Messaging channels | Live driver details, passenger numbers and location pins shared in WhatsApp groups with client travel desks. | Gap | High | s.8(5); Rule 6 | KAM HOD interview, 13 Oct 2026 | A1 | Open | 2026-11-13
G-004 | Sales | Messaging channels | Client contacts, driver requirements and booking requests shared on personal WhatsApp. | Gap | High | s.8(5); Rule 6 | Sales HOD interview, 13 Oct 2026 | A1 | Open | 2026-11-13
G-005 | CAT | Messaging channels | Dispatch details and passenger numbers sent to drivers and fleet vendors in WhatsApp groups and chats. | Gap | High | s.8(5); Rule 6 | CAT HOD interview, 12 Oct 2026 | A1 | Open | 2026-11-13
G-006 | VRM & Billing | ID masking | Full raw scans of Aadhaar, PAN, agreement, cancelled cheque, MSME and GST held on the Insta portal. | Gap | High | s.8(5); minimisation; UIDAI | VRM & Billing HOD interview, 08 Oct 2026 | A2 | Open | 2027-02-11
G-007 | Fleet | ID masking | Unmasked Aadhaar and raw document scans in application databases and backend portals. | Gap | High | s.8(5); minimisation; UIDAI | Fleet HOD interview, 08 Oct 2026 | A2 | Open | 2027-02-11
G-008 | HR | ID masking | Raw Aadhaar, PAN and bank passbook scans in file folders and Keka uploads. | Gap | High | s.8(5); minimisation; UIDAI | HR HOD interview, 14 Oct 2026 | A2 | Open | 2027-02-11
G-009 | Admin | ID masking | Answers conflict on whether guards copy visitor and contractor ID proofs. | Verify | Medium | s.8(5); minimisation; UIDAI | Admin HOD interview, 14 Oct 2026 | A2 | Open | 2027-02-11
G-010 | Accounts & Tax | ID masking | Aadhaar copies may be attached in billing back-up documents held in the ERP. | Verify | Medium | s.8(5); minimisation; UIDAI | Accounts & Tax HOD interview, 14 Oct 2026 | A2 | Open | 2027-02-11
G-011 | VRM & Billing | Local copies | Agents can download full KYC scans to local laptops. | Gap | High | s.8(5); Rule 6 | VRM & Billing HOD interview, 08 Oct 2026 | A3 | Open | 2027-02-11
G-012 | HR | Local copies | Payroll reconciliation, bank files, appraisal logs and employee lists stored on laptops. | Gap | Medium | s.8(5); Rule 6 | HR HOD interview, 14 Oct 2026 | A3 | Open | 2027-02-11
G-013 | KAM | Local copies | Client rosters, trip history and VIP files exported to local Excel; leaver risk. | Gap | Medium | s.8(5); Rule 6 | KAM HOD interview, 13 Oct 2026 | A3 | Open | 2027-02-11
G-014 | Sales | Local copies | CRM contact lists exportable to Excel; RFPs and pricing held locally; leaver risk. | Gap | Medium | s.8(5); Rule 6 | Sales HOD interview, 13 Oct 2026 | A3 | Open | 2027-02-11
G-015 | Admin | Local copies | Vendor, contractor and asset lists stored loose on desktop drives. | Gap | Medium | s.8(5); Rule 6 | Admin HOD interview, 14 Oct 2026 | A3 | Open | 2027-02-11
G-016 | Submission | Local copies | Raw duty slips and invoices kept on local drives for reconciliation (tracker score 2 of 5). | Gap | Medium | s.8(5); Rule 6 | Submission HOD interview, 08 Oct 2026 | A3 | Open | 2027-02-11
G-017 | Accounts & Tax | Local copies | Payout lists, TDS sheets and collection MIS exported to Excel on laptops (tracker score 2 of 5). | Gap | Medium | s.8(5); Rule 6 | Accounts & Tax HOD interview, 14 Oct 2026 | A3 | Open | 2027-02-11
G-018 | Reservations | Local copies | Bulk passenger manifests exported to local drives. | Gap | Medium | s.8(5); Rule 6 | Reservations HOD interview, 12 Oct 2026 | A3 | Open | 2027-02-11
G-019 | Fleet | Local copies | View-only access and disabled downloads stated as expected controls; not confirmed. | Verify | Medium | s.8(5); Rule 6 | Fleet HOD interview, 08 Oct 2026 | A3 | Open | 2027-02-11
G-020 | Collection | Local copies | DLP and disabled export claimed; summary says DLP must be enforced. Evidence needed. | Verify | Medium | s.8(5); Rule 6 | Collection HOD interview, 09 Oct 2026 | A3 | Open | 2027-02-11
G-021 | VRM & Billing | Retention | No purge scripts configured for post-contract driver and vendor data. | Gap | High | s.8(7); Rule 8 | VRM & Billing HOD interview, 08 Oct 2026 | A6 | Open | 2027-02-11
G-022 | HR | Retention | Rejected resumes and ex-employee profiles kept indefinitely in Keka and local folders. | Gap | Medium | s.8(7); Rule 8 | HR HOD interview, 14 Oct 2026 | A6 | Open | 2027-02-11
G-023 | KAM | Retention | Client rosters kept indefinitely in email archives and local drives. | Gap | Medium | s.8(7); Rule 8 | KAM HOD interview, 13 Oct 2026 | A6 | Open | 2027-02-11
G-024 | Sales | Retention | Lost leads and RFP contacts kept indefinitely in the CRM. | Gap | Medium | s.8(7); Rule 8 | Sales HOD interview, 13 Oct 2026 | A6 | Open | 2027-02-11
G-025 | Admin | Retention | Visitor logs and CCTV footage kept until storage fills; no purge schedule. | Gap | Medium | s.8(7); Rule 8 | Admin HOD interview, 14 Oct 2026 | A6 | Open | 2027-02-11
G-026 | Fleet | Retention | Automated purge after statutory period claimed; VRM says none is configured. | Verify | Medium | s.8(7); Rule 8 | Fleet HOD interview, 08 Oct 2026 | A6 | Open | 2027-02-11
G-027 | CAT | Retention | Central retention schedule referenced; not seen. App cache purge stated. | Verify | Low | s.8(7); Rule 8 | CAT HOD interview, 12 Oct 2026 | A6 | Open | 2027-02-11
G-028 | Marketing | Retention | 3-month lead validity and auto-suppression claimed; not evidenced. | Verify | Medium | s.8(7); Rule 8 | Marketing HOD interview, 12 Oct 2026 | A6 | Open | 2027-02-11
G-029 | Submission | Retention | 30-day link expiry stated; wider retention not covered. | Verify | Low | s.8(7); Rule 8 | Submission HOD interview, 08 Oct 2026 | A6 | Open | 2027-02-11
G-030 | Collection | Retention | 8-year retention then archive or delete; process unclear. | Verify | Low | s.8(7); Rule 8 | Collection HOD interview, 09 Oct 2026 | A6 | Open | 2027-02-11
G-031 | Accounts & Tax | Retention | 8 financial years; deletion is manual, automation in progress. | Verify | Low | s.8(7); Rule 8 | Accounts & Tax HOD interview, 14 Oct 2026 | A6 | Open | 2027-02-11
G-032 | Reservations | Retention | 90-day post-trip retention stated; not evidenced. | Verify | Low | s.8(7); Rule 8 | Reservations HOD interview, 12 Oct 2026 | A6 | Open | 2027-02-11
G-033 | CMT | Retention | Contract plus 8 years; no automated disposal described. | Verify | Low | s.8(7); Rule 8 | CMT HOD interview, 12 Oct 2026 | A6 | Open | 2027-02-11
G-034 | VRM & Billing | Vendor DPAs | NDA and DPA templates follow GDPR terms; none signed with fleet vendors. | Gap | High | s.8(2) | VRM & Billing HOD interview, 08 Oct 2026 | A7 | Open | 2027-02-11
G-035 | Fleet | Vendor DPAs | No signed NDA or DPA with vendors; revenue-share contracts only. | Gap | High | s.8(2) | Fleet HOD interview, 08 Oct 2026 | A7 | Open | 2027-02-11
G-036 | HR | Vendor DPAs | Keka and Mynd contracts lack processor duties and breach notice; HR flow record says DPA signed. | Gap | High | s.8(2) | HR HOD interview, 14 Oct 2026 | A7 | Open | 2027-02-11
G-037 | Sales | Vendor DPAs | Legacy client MSAs carry NDAs only; no data rights, purpose limits or breach timelines. | Gap | High | s.8(2) | Sales HOD interview, 13 Oct 2026 | A7 | Open | 2027-02-11
G-038 | Admin | Vendor DPAs | Security, janitorial and maintenance vendor contracts lack processor duties. | Gap | Medium | s.8(2) | Admin HOD interview, 14 Oct 2026 | A7 | Open | 2027-02-11
G-039 | Marketing | Vendor DPAs | Agency and platform DPAs not yet evidenced. | Verify | Medium | s.8(2) | Marketing HOD interview, 12 Oct 2026 | A7 | Open | 2027-02-11
G-040 | Accounts & Tax | Vendor DPAs | Auditor and software vendor DPAs being updated by Legal. | Verify | Medium | s.8(2) | Accounts & Tax HOD interview, 14 Oct 2026 | A7 | Open | 2027-02-11
G-041 | VRM & Billing | Notice & consent | No privacy notice served to drivers and vendors; no version history; no withdrawal mechanism (tracker score 0 of 5). | Gap | High | s.5, s.6; Rule 3 | VRM & Billing HOD interview, 08 Oct 2026 | A5 | Open | 2027-02-11
G-042 | Marketing | Notice & consent | Opt-in and unsubscribe described but marked 'not available as of now'. | Gap | High | s.5, s.6; Rule 3 | Marketing HOD interview, 12 Oct 2026 | A5 | Open | 2027-02-11
G-043 | Fleet | Notice & consent | Consent letter handled in the VRM flow; notice not evidenced. | Verify | Medium | s.5, s.6; Rule 3 | Fleet HOD interview, 08 Oct 2026 | A5 | Open | 2027-02-11
G-044 | Accounts & Tax | Notice & consent | No independent notice for sub-ledger processing; relies on VRM and contracts. | Verify | Low | s.5, s.6; Rule 3 | Accounts & Tax HOD interview, 14 Oct 2026 | A5 | Open | 2027-02-11
G-045 | HR | Cross-border | Keka backups, analytics plug-ins and payroll vendor hosting unknown. | Verify | Medium | s.16 | HR HOD interview, 14 Oct 2026 | A9 | Open | 2027-05-12
G-046 | Sales | Cross-border | CRM hosting region unconfirmed. | Verify | Medium | s.16 | Sales HOD interview, 13 Oct 2026 | A9 | Open | 2027-05-12
G-047 | Marketing | Cross-border | Transfers confirmed via Google Ads, Meta Ads and app.chati.ai; assess against Section 16. | Verify | Medium | s.16 | Marketing HOD interview, 12 Oct 2026 | A9 | Open | 2027-05-12
G-048 | Submission | Cross-border | Drive and OneDrive links; audit notes a possible US host. | Verify | Medium | s.16 | Submission HOD interview, 08 Oct 2026 | A9 | Open | 2027-05-12
G-049 | Reservations | Cross-border | Google Workspace and AWS: answered No but scope flags conditional risk. | Verify | Medium | s.16 | Reservations HOD interview, 12 Oct 2026 | A9 | Open | 2027-05-12
G-050 | VRM & Billing | Consent | VRM agents tick and sign onboarding consent in CabPro on behalf of vendors; conflicts with Section 6 (tracker score 1 of 5). | Gap | Critical | s.6 | VRM & Billing HOD interview, 08 Oct 2026 | A4 | Open | 2027-02-11
G-051 | VRM & Billing | Data accuracy | No automated alert for expiring driver and vehicle documents (tracker score 2 of 5). | Gap | Medium | s.8(3) | VRM & Billing HOD interview, 08 Oct 2026 | A1 | Open | 2026-11-13
G-052 | Collection | Sharing & minimisation | MIS with booking IDs and guest names sent to clients on request. | Gap | Medium | s.8(5) | Collection HOD interview, 09 Oct 2026 | A8 | Open | 2026-11-13
G-053 | Accounts & Tax | Sharing & minimisation | Tax schedules, TDS certificates and payment proofs sent to external auditors as loose email attachments; MIS with guest names. | Gap | High | s.8(5) | Accounts & Tax HOD interview, 14 Oct 2026 | A8 | Open | 2026-11-13
G-054 | KAM | Sharing & minimisation | Client MIS carries names, phones and full route logs; VIP files unencrypted and emailed. | Gap | High | s.8(5) | KAM HOD interview, 13 Oct 2026 | A8 | Open | 2026-11-13
G-055 | Submission | Sharing & minimisation | Invoices shared by Drive/OneDrive links and unencrypted ZIPs (medium-high risk in tracker). | Gap | High | s.8(5) | Submission HOD interview, 08 Oct 2026 | A8 | Open | 2026-11-13
G-056 | Sales | Sharing & minimisation | VIP and executive profiles kept in unencrypted Word/Excel files sent by email. | Gap | Medium | s.8(5) | Sales HOD interview, 13 Oct 2026 | A8 | Open | 2026-11-13
G-057 | Admin | Physical records | Paper visitor register left open; later visitors can read earlier entries. | Gap | High | s.8(5) | Admin HOD interview, 14 Oct 2026 | A10 | Open | 2026-11-13
G-058 | Reservations | Incident response | Incident-response question left unanswered in the interview. | Verify | Medium | s.8(6); Rule 7 | Reservations HOD interview, 12 Oct 2026 | A11 | Open | 2027-05-12
Formulas:
Target date = IFERROR(INDEX('Action Tracker'!$F5:F15,MATCH([Action ID],'Action Tracker'!$A5:A15,0)),"")

## Action Tracker
Action Tracker
Due date = programme start (Dashboard) + target day. Linked and open findings count from the Gap Register.
ID | Action | Owner (function) | Phase | Target day | Due date | Departments in scope | Linked findings | Open findings | Status | % complete | Named owner | Evidence / link | Remarks
A1 | Ban WhatsApp for personal data; ship CabPro Android upload and driver-app dispatch with masked numbers | IT, Fleet Ops | 1 Contain | 30 | 2026-11-13 | CAT, Fleet, VRM, KAM, Sales | 6 | 6 | Not started | 0%
A2 | Mask Aadhaar at ingestion (redact first 8 digits); stop raw image storage; redact existing scans | IT | 2 Build | 120 | 2027-02-11 | Fleet, VRM, HR (verify Admin, Accounts & Tax) | 5 | 5 | Not started | 0%
A3 | Deploy endpoint DLP; set systems to view-only; disable bulk export in ERP and CRM | IT Security | 2 Build | 120 | 2027-02-11 | VRM, HR, KAM, Sales, Admin, Submission, Accounts & Tax, Reservations | 10 | 10 | Not started | 0%
A4 | Rebuild consent: vendor or driver signs by OTP or eSign, time-stamped; stop agent-signed consent | IT, VRM | 2 Build | 120 | 2027-02-11 | VRM, Fleet | 1 | 1 | Not started | 0%
A5 | Publish versioned bilingual privacy notice and a withdrawal path (incl. marketing opt-in and unsubscribe) | DPO, IT | 2 Build | 120 | 2027-02-11 | VRM, Fleet, Marketing | 4 | 4 | Not started | 0%
A6 | Approve the retention schedule; automate purge | DPO, IT | 2 Build | 120 | 2027-02-11 | All 13 | 13 | 13 | Not started | 0%
A7 | Issue a DPDP-ready DPA; execute with vendors and client MSAs | Legal | 2 Build | 120 | 2027-02-11 | Fleet, VRM, HR, Sales, Admin, Accounts & Tax, Marketing | 7 | 7 | Not started | 0%
A8 | Mask names in client MIS; named, expiring links, encrypted ZIPs and a data room for auditors | Billing, KAM leads | 1 Contain | 30 | 2026-11-13 | Submission, Collection, Accounts & Tax, KAM | 5 | 5 | Not started | 0%
A9 | Close cross-border checks on Keka/Mynd, ad platforms, Workspace, Drive/OneDrive, CRM | IT, Legal | 3 Sustain | 210 | 2027-05-12 | HR, Marketing, Reservations, Submission, Sales | 5 | 5 | Not started | 0%
A10 | Cover the visitor register; set CCTV and access-log retention | Admin | 1 Contain | 30 | 2026-11-13 | Admin | 1 | 1 | Not started | 0%
A11 | Update breach SOP for a 72-hour Board report; run a drill; train staff by role | DPO, IT Security | 3 Sustain | 210 | 2027-05-12 | All 13 | 1 | 1 | Not started | 0%
Blue text on yellow = input. Target day is an assumption from the roadmap; change it to re-plan. Overdue due dates turn red.
Formulas:
Due date = Dashboard!$C4+[Target day]

## Retention Schedule
Retention Schedule (proposed)
Basis type: Statutory floor = a law sets a minimum. Stated in interview = the HOD gave the period. Proposed = no statute found; set under DPDP s.8(7) on purpose. Proposed periods are recommendations for Legal and the DPO to approve.
ID | Data category | Departments | Data principals | Clock starts | Statutory minimum | Proposed retention | Basis type | Disposal | Current practice (interviews) | ROPA ID | Owner | Status | Approved by Legal | Notes
T-01 | Books of account, invoices, vouchers, duty slips supporting invoices | Accounts & Tax, Collection, Submission | Clients, drivers, vendors, guests | End of financial year | 8 financial years (Companies Act s.128(5)); GST 72 months; Income-tax 6 years | 8 financial years, then delete or anonymise. Mask guest phone numbers on duty slips after 90 days. | Statutory floor | Secure delete; restricted archive | 8 years stated; deletion manual; guest names in MIS | R-08, R-09, R-10 | Accounts & Tax head | Proposed | No
T-02 | Vendor and driver payout data (bank, PAN, TDS records) | Accounts & Tax | Drivers, vendors | End of FY of last payment | 8 financial years as voucher support | 8 financial years from the FY of last payment, then delete. | Statutory floor | Secure delete | 8 years stated; manual deletion | R-10 | Accounts & Tax head | Proposed | No
T-03 | Driver and vendor KYC scans (Aadhaar, DL, RC, insurance, permits) | Fleet, VRM | Chauffeurs, vehicle owners, vendors | Relationship end | None found for raw copies | Relationship end + 3 years (claims window). Store Aadhaar masked only. Keep only masked copies as payout support. | Proposed | Automated purge job | No purge configured (VRM); Fleet claims automated | R-01 | Fleet / VRM heads | Proposed | No
T-04 | Consent records and privacy notice versions | VRM, Fleet, Marketing | All data principals | Consent withdrawn or relationship end | None | Life of consent + 3 years, as evidence. | Proposed | Secure delete | No notice or version history today | R-01, R-07 | DPO | Proposed | No
T-05 | Booking and dispatch records (name, phone, pickup, drop) | Reservations, CAT, KAM | Passengers, corporate employees | Trip completion | None | 90 days after trip, then remove identifiers. Billing copy is kept under T-01. | Stated in interview | Automated archive then delete | Reservations: 90 days stated; KAM rosters indefinite | R-02, R-03, R-04 | Reservations / CAT heads | Proposed | No
T-06 | Driver app, trip and location logs | CAT, IT | Passengers, chauffeurs | Date of processing | At least 1 year (DPDP Rule 8(3)) | 1 year, then delete unless an incident or claim is open. | Statutory floor | Automated purge | App cache purged post-trip; central retention not seen | R-02 | IT | Proposed | No
T-07 | System, access and security logs | IT Security | All | Date of log | 180 days in India (CERT-In); at least 1 year (DPDP Rule 8(3)) | 1 year (the longer rule), stored in India. | Statutory floor | Automated rotation | Not covered in interviews |  | IT Security | Proposed | No
T-08 | Corporate client contacts and contract files | CMT, Sales, KAM | Client signatories, travel desks | Contract end | 8 financial years where part of books | Contract end + 8 years for contract and billing file. Deactivate a contact when the client confirms a change. | Stated in interview | Secure delete | CMT states contract + 8 years | R-05, R-06 | CMT head | Proposed | No
T-09 | Client rosters, MIS exports, VIP profiles | KAM, Sales | Client employees, VIPs | Account termination | None | Delete within 90 days of account termination. No local exports. | Proposed | Delete from CRM, email and laptops | Indefinite in email and local drives | R-04, R-05 | KAM / Sales heads | Proposed | No
T-10 | Lost or unconverted B2B leads and RFP contacts | Sales | Prospect contacts | Last contact | None | 12 months from last contact, then delete. | Proposed | Automated CRM purge | Indefinite in CRM | R-05 | Sales head | Proposed | No
T-11 | Marketing leads, app and campaign data | Marketing | Leads, app users | Last engagement | None | 3 months idle (Marketing's figure). Erase on consent withdrawal. | Stated in interview | Automated suppression and delete | 3-month validity claimed; not evidenced | R-07 | Marketing head | Proposed | No
T-12 | Marketing opt-out (suppression) list | Marketing | Leads, customers | Opt-out date | None | Keep the minimum identifier needed to honour the opt-out. | Proposed | Review yearly | Unsubscribe 'not available as of now' | R-07 | Marketing head | Proposed | No
T-13 | Payroll, PF, ESIC and tax records | HR | Employees | End of financial year | 8 FY stated by HR; labour-law periods not verified | 8 financial years. HR and Legal to confirm any longer statutory period. | Stated in interview | Secure delete | 8 years stated | R-11 | HR head | Proposed | No
T-14 | Employee personnel file and appraisals | HR | Employees | Exit date | None found | Exit + 3 years, then delete. | Proposed | Secure delete | Held indefinitely | R-11 | HR head | Proposed | No
T-15 | Rejected applicant resumes | HR | Applicants | Rejection | None | 12 months. Longer only with consent for a talent pool. | Stated in interview | Automated purge in Keka | Indefinite in Keka and local folders | R-11 | HR head | Proposed | No
T-16 | Ex-employee HRMS profile and access | HR, IT | Ex-employees | Exit date | Statutory payroll records only | Revoke access on exit day. Keep only the records under T-13 and T-14. | Proposed | Access revocation checklist | Profiles remain in Keka indefinitely | R-11 | HR / IT | Proposed | No
T-17 | Visitor registers and gate records | Admin | Visitors, contractors | Visit date | None | 12 months. Paper register must not be left open. | Proposed | Shred or delete | Indefinite; register open to later visitors | R-12 | Admin head | Proposed | No
T-18 | CCTV footage | Admin | Staff, visitors | Recording date | None | 90 days. Hold longer only for a flagged incident. | Proposed | Automatic overwrite | Kept until storage fills | R-12 | Admin head | Proposed | No
T-19 | Biometric and access-card logs | Admin, HR | Employees, visitors | Date of log | Possibly Rule 8(3), 1 year; confirm with Legal | 1 year. Attendance summaries are kept under T-13. | Proposed | Automated purge | No documented purge | R-11, R-12 | Admin / HR | Proposed | No
T-20 | Facility vendor contacts and details | Admin | Vendor owners | Contract end | 8 FY for payment records (T-01) | Contacts: contract end + 1 year. Payment records under T-01. | Proposed | Delete from desktop files | Loose Excel on desktops | R-12 | Admin head | Proposed | No
T-21 | Shared cloud links for invoices and duty slips | Submission | Billing contacts, passengers on slips | Link creation | None | 30 days maximum, named recipients, password. | Stated in interview | Link expiry | 30 days approved by HOD; links not always restricted | R-08 | Submission head | Proposed | No
T-22 | Breach register and incident records | DPO, IT Security | Affected principals | Incident closure | None | 3 years after closure. Keep the Board report copy as long. | Proposed | Secure delete | Register exists per HODs; not seen |  | DPO | Proposed | No
T-23 | Data principal requests (access, correction, erasure, withdrawal) | DPO | Requesters | Request closure | None | 3 years after closure. | Proposed | Secure delete | No workflow today |  | DPO | Proposed | No
T-24 | Contracts, NDAs and DPAs | Legal, CMT, Fleet | Signatories | Termination | None | Termination + 8 years (CMT's contractual liability figure). | Stated in interview | Secure delete | Not defined outside CMT | R-06 | Legal | Proposed | No

## Retention Rules
Retention Rules: what applies to Carzonrent
Bottom line: the DPDP Act sets no fixed retention period for a company like Carzonrent. Section 8(7) requires erasure once the purpose is served or consent is withdrawn, unless another law requires retention. So Carzonrent must set its own purpose-based periods, and keep tax, company-law and log records for the periods those laws require.
Rule | What it says | Applies to Carzonrent? | What to do | Source | Verified?
DPDP Act s.8(7) | Erase personal data when consent is withdrawn or it is reasonable to assume the purpose is no longer served, unless retention is necessary to comply with a law. No fixed period. | Yes, from about May 2027 | Set a purpose-based period for every data category (Retention Schedule). Document the reason. Automate deletion. | DPDP Act 2023; summary at sansalegal.com (DPDP Rules 2025 retention schedule guide) | Checked against a secondary source
DPDP Rules 2025, Rule 8(1) and Third Schedule | Fixed 3-year period (from the user's last interaction) for e-commerce entities with 2 crore or more users, online gaming intermediaries with 50 lakh or more, and social media intermediaries with 2 crore or more. | Very unlikely. Confirm registered-user count and that Carzonrent is not an e-commerce entity at that scale. | No fixed 3-year period applies. Use the company schedule. | DPDP Rules 2025 via sansalegal.com | Checked against a secondary source; Legal to confirm
DPDP Rules 2025, Rule 8(2) | 48 hours' notice to the user before erasure, for the Third Schedule classes. | Not required for Carzonrent on the above | Optional good practice for customer-facing erasure. | sansalegal.com | Checked against a secondary source
DPDP Rules 2025, Rule 8(3) | Retain personal data, associated traffic data and processing logs for at least one year, for the purposes the Rules specify. | Yes, for logs | Keep processing, access and trip logs at least 1 year, then delete unless another law needs longer. | sansalegal.com | Checked against a secondary source; Legal to confirm scope
DPDP Act s.6(6) and s.12(3) | On withdrawal of consent, stop processing (and make processors stop). On a user's erasure request, erase unless needed for the purpose or to comply with law. | Yes | Build a withdrawal and erasure workflow, including fleet vendors and other processors. | sansalegal.com | Checked against a secondary source
Companies Act 2013 s.128(5) | Books of account and vouchers: at least the 8 financial years immediately preceding the current one. | Yes | Keep books, invoices, vouchers and supporting duty slips for 8 financial years. | metalegal.in (maintenance of records) | Checked against a secondary source
Income-tax Rules 1962, Rule 6F(5) | Books and documents: at least 6 years from the end of the relevant assessment year. | Yes, but the Income-tax Act 2025 replaces the 1961 Act from 1 April 2026; confirm the equivalent rule | The 8-year Companies Act period is longer, so 8 financial years covers it. | metalegal.in | Checked for the 1961 Act only; Legal to confirm under the 2025 Act
CGST Act s.36 and Rule 56 | Accounts and records: 72 months from the due date of the annual return for the year; longer if proceedings are pending. | Yes | Covered by the 8-year books period; extend for pending proceedings. | taxguru.in / metalegal.in | Checked against a secondary source
CERT-In Directions 2022 | Keep ICT system logs for a rolling 180 days within India; report cyber incidents within 6 hours. | Yes | Keep logs 1 year (the longer DPDP floor), stored in India. | mondaq.com (overview of CERT-In directions) | Checked against a secondary source
Labour laws (PF, ESIC, Gratuity, Payment of Wages, Contract Labour) | Record-keeping periods differ by statute. | Yes for employees | HR and Legal to list the exact period per statute. Until then HR's stated 8 financial years applies. | Not verified in this review | NOT verified
Limitation Act 1963 | General limitation of 3 years for most civil claims. | Used as the basis for dispute windows (proposal, not a retention rule) | Used to justify relationship end + 3 years for KYC, consent and personnel records. Legal to confirm. | General legal principle | Not verified here; Legal to confirm

## ROPA
ROPA: Record of Processing Activities
Lawful basis is proposed for Legal to confirm. Retention is as stated by the HOD. Yellow cells are for owners to complete.
ROPA ID | Department | Processing activity | Data principals | Data categories | Purpose | Proposed lawful basis | Systems | Recipients | Cross-border | Retention (as stated) | Retention gap? | Owner (HOD) | Last reviewed | Status
R-01 | Fleet, VRM | Driver and vendor onboarding | Chauffeurs, vehicle owners, fleet vendors | Aadhaar, PAN, DL, bank details, RC, insurance, fitness/permits, cancelled cheque, consent letter, contact details | Verify eligibility, TDS and payouts, vendor contracts | Consent (s.6) plus legal obligation (tax) | CabPro, Insta portal | Accounts, Allocation | No | 8 years for tax; automated purge not built | Yes |  |  | Draft
R-02 | CAT | Trip allocation and dispatch | Passengers, chauffeurs | Passenger name and phone, pickup and drop, chauffeur name, phone and DL number, vehicle | Allocate cars, dispatch drivers, passenger safety | Voluntary provision for the requested service (s.7) | Dispatch system, driver app, WhatsApp (to retire) | Fleet vendors, chauffeurs | Not asked | Central retention schedule; app cache purged post-trip | To verify |  |  | Draft
R-03 | Reservations | Corporate booking intake | Corporate employees | Name, phone, pickup and drop, flight or train details, travel time, special instructions, billing identifiers | Arrange transport, calculate ETAs, billing | Voluntary provision for the requested service (s.7) | Google Workspace mail, booking software | KAM, Ops, client travel desk | To verify | 90 days after trip (stated) | To verify |  |  | Draft
R-04 | KAM | Key account servicing | Client travel desks, employees, VIPs | Contacts, employee ID, cost centre, itineraries, flight numbers, VIP preferences, driver assignment | Bookings, escalations, MIS, account reviews | Voluntary provision for the requested service (s.7) | Insta ERP, email, WhatsApp groups (to retire) | Dispatch, client travel desks | No | Billing 8 years; rosters and logs indefinite | Yes |  |  | Draft
R-05 | Sales | B2B sales and RFPs | Travel managers, procurement officers | Name, designation, email, phone, address, GSTIN, corporate bank details | Evaluate bids, negotiate rate contracts, set up billing | Contract; voluntary provision (s.7) | CRM, Insta ERP, email, WhatsApp (to retire) | CMT, Ops, Billing | To verify | Contract plus 8 years; lost leads indefinite | Yes |  |  | Draft
R-06 | CMT | Corporate contract management | Authorised signatories | Name, email, phone, designation, contract and billing terms, GST copy | Execute B2B agreements, create client in Insta ERP, collections | Contract | Insta ERP, CMT file server, SRM archive | Accounts, KAM, Legal, Sales | No | Contract plus 8 years | To verify |  |  | Draft
R-07 | Marketing | Campaigns and lead generation | Leads, app users, event registrants | Name, phone, email, location, vehicle preference, booking history, app behaviour, response logs | Targeted offers, loyalty programmes, ROI analysis | Consent (s.6) | Insta CRM, app.chati.ai, Google Ads, Meta Ads, email providers | Ad networks, email gateways, Sales | Yes | 3 months for idle leads (stated) | To verify |  |  | Draft
R-08 | Submission | Invoice submission | Corporate billing contacts, passengers, chauffeurs | Billing contacts, passenger and chauffeur details on duty slips, vehicle numbers, payment schedules | Corporate billing, trip validation, client audit | Contract | Insta ERP, email, courier, Drive/OneDrive links | Corporate client billing teams | To verify | Shared links expire in 30 days | To verify |  |  | Draft
R-09 | Collection | Collections and reconciliation | Client contacts, guests | Contact details, guest names in MIS, bank details, transaction IDs, remittance advice | Payment follow-up, reconciliation, tax invoices | Contract; legal obligation | Oracle ERP, Insta ERP, email | Finance, financial auditors | No | 8 financial years | To verify |  |  | Draft
R-10 | Accounts & Tax | Payouts, TDS and GST | Drivers, vendors, employees | Bank account, IFSC, PAN, GSTIN, trip earnings, TDS records, reimbursement claims | Vendor payouts, TDS and GST returns, audits | Legal obligation (s.7) | Oracle ERP, Insta ERP | Banks, GSTN, TRACES, financial auditors | No | 8 financial years; deletion manual | Yes |  |  | Draft
R-11 | HR | Recruitment, payroll and attendance | Employees, applicants | Name, DOB, address, Aadhaar, PAN, bank, PF and ESIC numbers, health insurance, attendance, appraisals | Payroll, statutory dues, insurance, performance | Employment and legal obligation (s.7) | Keka HRMS, Mynd Solutions, biometric | PF, ESIC, tax authorities, banks | To verify | Payroll 8 years; resumes and ex-employee files indefinite | Yes |  |  | Draft
R-12 | Admin | Visitor, facility and asset records | Visitors, contractors, facility vendors | Name, phone, email, company, ID details, vehicle number, photo, vendor bank details, asset allocation | Site security, access control, vendor payments | Voluntary provision; contract (s.7) | Paper register, biometric, CCTV, Excel | Facility and security vendors | No | CCTV and logs kept indefinitely | Yes |  |  | Draft
Still to capture: retail bookings (CRM mailbox), app and web bookings, Finance payouts team, IT, Legal. Add rows below as they are interviewed.

## Departments
Department status
Rating is preliminary (reviewer's synthesis). Counts are live from the Gap Register.
Department | Interview date | Preliminary rating | Gaps | Verify items | Open findings | Action tracker in form | HOD declaration signed | Evidence pack received | Key issue
VRM & Billing | 2026-10-08 | Critical | 8 | 0 | 8 | Completed | No | No | Agents sign consent for vendors; no notice; raw Aadhaar; WhatsApp intake; no valid DPA.
Fleet | 2026-10-08 | Critical | 3 | 3 | 6 | Blank | No | No | Unmasked Aadhaar in databases; KYC over WhatsApp; no NDA or DPA with vendors.
HR | 2026-10-14 | High | 4 | 1 | 5 | Blank | No | No | Raw ID scans; payroll files on laptops; resumes kept indefinitely; vendor terms and hosting.
KAM | 2026-10-13 | High | 4 | 0 | 4 | Blank | No | No | WhatsApp groups with clients; VIP files unencrypted; rosters kept indefinitely; bulk export.
Sales | 2026-10-13 | High | 5 | 1 | 6 | Blank | No | No | WhatsApp with clients; NDA-only MSAs; CRM export open; lost leads never purged.
CAT | 2026-10-12 | High | 1 | 1 | 2 | Blank | No | No | Dispatch with passenger numbers goes out over WhatsApp groups and chats.
Marketing | 2026-10-12 | High | 1 | 3 | 4 | Not in form | No | No | Consent and unsubscribe not in place; cross-border platforms; agency DPAs unseen.
Admin | 2026-10-14 | High | 4 | 1 | 5 | Blank | No | No | Open visitor register; CCTV kept until full; vendor lists on desktops; ID answers conflict.
Submission | 2026-10-08 | Medium | 2 | 2 | 4 | Completed | No | No | Drive links and unencrypted ZIPs; duty slip copies on desktops.
Accounts & Tax | 2026-10-14 | Medium | 2 | 4 | 6 | Completed | No | No | Auditor files by loose email (High item); exports on laptops; manual deletion.
Collection | 2026-10-09 | Medium | 1 | 2 | 3 | Not in form | No | No | Guest names in MIS on request; DLP claimed but not evidenced.
Reservations | 2026-10-12 | Medium | 1 | 3 | 4 | Not in form | No | No | Manifests exported to laptops; mail region unconfirmed; incident answer blank.
CMT | 2026-10-12 | Low | 0 | 1 | 1 | Blank | No | No | Restricted server and locked archives; hand-offs by email only.
Total |  |  | 36 | 22 | 58

## Lists
Lists and assumptions
Finding status | Action status | Rating / priority | Yes / No / Partial | Type | ROPA status | Departments | Retention status
Open | Not started | Critical | Yes | Gap | Draft | VRM & Billing | Draft
In progress | In progress | High | No | Verify | Reviewed by owner | Fleet | Proposed
Evidence received | Blocked | Medium | Partial |  | Approved by Legal | Submission | Approved by Legal
Closed | Complete | Low |  |  |  | Collection | Implemented
CAT
CMT
Marketing
Reservations
Sales
KAM
Assumptions and sources | [5 empty] | Accounts & Tax
1. Findings, ratings and ROPA content come from 13 HOD interviews held 8 to 14 October 2026. | [5 empty] | Admin
2. Priority and preliminary department ratings are the reviewer's synthesis, not auditor scores. Only VRM, Submission and Accounts & Tax trackers carried auditor scores. | [5 empty] | HR
3. Gap = confirmed in the interview. Verify = control claimed or risk conditional; evidence needed.
4. Target days follow the roadmap: Day 30 Contain, Day 120 Build, Day 210 Sustain. Day 210 from 14 Oct 2026 is 12 May 2027.
5. Main DPDP Rules duties start about 13 May 2027 (18 months from notification on 13 Nov 2025). Source: DPDP Rules 2025 via Mondaq. Legal to confirm.
6. DPDP section and rule references are indicative. Legal to confirm.
7. Proposed lawful bases in the ROPA are for Legal to confirm.